## ACTION ITEMS
Notes on Accessibility: Tested and Best Accessible Through JAWS Version 11 or Higher. For definitions, please refer to the worksheet labeled DEFINITIONS.
FUNDING No: |  | FULL PROJECT NAME: |  | PROJECT MANAGER: |  |  | TECHNOLOGY DEPLOYED:
PRINT ON LEGAL SIZE PAPER
ACTION ITEM No. | DATE OPENED | DESCRIPTION | PRIORITY | RESPONSIBLE PARTY | DUE DATE | COMPLETION DATE | NOTES | STATUS
1 | 2023-10-16 | Creazione Logo | L | Salvatore Mattiello | 2023-10-16 | 2023-10-23 | E' stata affidata la creazione a Salvatore, ma anche altri membri possono partecipare | Closed
2 | 2023-10-16 | Chiarimenti criteri di premialità con Prof. Ferrucci | M | Vincent Milione | 2023-10-17 | 2023-10-17 | I membri della nostra squadra quanto verranno premiati per usare delle tecnologie innovative? | Closed
3 | 2023-10-16 | Discussione modulo di intelligenza artificiale con Prof. Palomba | M | Daniele Donia | 2023-10-16 | 2023-10-16 | Che tipo di modello si potrebbe pensare di realizare in base all'idea progettuale proposta? | Closed
4 | 2023-10-23 | Creazione scenario as-is per vendita tramite mercati | H | Michele Martino | 2023-10-27 | 2023-10-27 | NA | Closed
5 | 2023-10-23 | Creazione scenario as-is per vendita tramite Marketplace | H | Salvatore Mattiello | 2023-10-27 | 2023-10-27 | NA | Closed
6 | 2023-10-23 | Creazione Scenario as-is vendita tramite e-commerce | H | Giuseppe di Sarno | 2023-10-27 | 2023-10-27 | NA | Closed
7 | 2023-10-30 | Creazione scenari relativi alla gestione del catalogo dei prodotti | H | Maura Pasquariello | 2023-11-06 | 2023-11-06 | NA | Closed
8 | 2023-10-30 | Creazione scenario registrazione profilo agricoltore | H | Michele Martino | 2023-11-06 | 2023-11-07 | NA | Closed
9 | 2023-10-30 | Creazione scenario gestione scadenza certificati | H | Giovanni de Gregorio | 2023-11-06 | 2023-11-08 | NA | Closed
10 | 2023-10-30 | Creazione scenario caricamento nuovo certificato | H | Giovanni de Gregorio | 2023-11-06 | 2023-11-09 | NA | Closed
11 | 2023-10-30 | Creazione scenario preparazione ordine dell’agricoltore | H | Giovanni de Gregorio | 2023-11-06 | 2023-11-10 | NA | Closed
12 | 2023-10-30 | Creazione scenario di richiesta e accettazione di partecipazione al mercato | H | Davide Califano | 2023-11-06 | 2023-11-11 | NA | Closed
13 | 2023-10-30 | Creazione scenari degli acquisti | H | Salvatore Mattiello | 2023-11-06 | 2023-11-12 | NA | Closed
14 | 2024-12-31 | Sistemazione pom.xml | M | Davide Califano | 2023-02-01 | 2023-02-01 | plugin di jacoco non esporta i report sulle coverage correttamente | Closed
1 | 2023-10-16 | Creazione Logo | H | Salvatore Mattiello | 2023-10-16 | 2023-10-23 | E' stata affidata la creazione a Salvatore, ma anche altri membri possono partecipare | Closed
2 | 2023-10-16 | Chiarimenti criteri di premialità con Prof. Ferrucci | H | Vincent Milione | 2023-10-17 | 2023-10-17 | I membri della nostra squadra quanto verranno premiati per aver | Closed
3 | 2023-10-16 | Discussione modulo di intelligenza artificiale con Prof. Palomba | H | Daniele Donia | 2023-10-16 | 2023-10-16 | NA | Closed

## Sheet3 (hidden)
Technical
Sponsorship
Communications
Schedule
Budget
Contracts
Scope
Accept
Transfer
Mitigate
Avoid
Share
Exploit
Enhance

## DEFINITIONS
FUNDING No.
The funding number is assigned by the OFM (Office of Financial Management) once the project is approved for funding.
This Link Takes You to Funding No. in the Template
PROJECT MANAGER
Individual responsible for creating, updating and maintaining the integrity of the action items list. Individual assigned with the responsibility of documenting action items and orchestrating updates to the action items list with those responsible and accountable for their assigned action items.
This Link Takes You to Project Manager in the Template
TECHNOLOGY DEPLOYED
Technology deployed is the category or component of a system under development in this project. The categories of technologies currently available are Mid-tier (application), Desktop, Mainframe, Database, Infrastructure, Office Automation or Telecommunications.
This Link Takes You Technology Deployed in the Template
ACTION ITEM No.
A unique identifier in a numbering system assigned to an action item. The identifier should be used for reference or for cross-reference in the future to navigate through action items. Example: AI01, AI02, AI03...
This Takes You to Action Item No in the Template
DATE OPENED
The date that the action was deemed necessary through a collective approach. A collective approach is used when tasks - that need to be completed - are identified by project stakeholders, and there's a mutual agreement that these tasks will be carried out by the individual responsible for the action item.
This Link Takes You to Date Opened in the Template
DESCRIPTION
An action item is a cooperative agreement among project stakeholders that a certain action need to take place to carry out a project. An example of an action item description is "To correct errors identified on three web pages before proceeding into the implementation phase." In this case, the action item is necessary to be completed prior to entering the implementation phase as members have proposed in a meeting.
This Link Takes You to Description in the Template
PRIORITY
The level of priority in this case addresses which action items are the most sensitive to the project, and need to be resolved with the highest level of attention and/or precedence. Depending on the project, action items are to be addressed with timeliness, highest degree of focus and/or tactfulness. "H" denotes High Priority. "M" denotes "Medium Priority." "L" denotes "Low Priority."
This Link Takes You to Priority in the Template
RESPONSIBLE PARTY
The individual responsible for ensuring that an action item is carried out in the agreed upon manner.
This Link Takes You to Responsible Party in the Template
DUE DATE
The date the action item is expected to be closed.
This Link Takes You to Due Date in the Template
COMPLETION DATE
The actual date the action item was closed.
This Link Takes You to Completion Date in the Template
NOTES
Progress of an action item to date. Start with the date, and then briefly describe what has been accomplished. EXAMPLE: "MM/DD/YYYY - Enter Notes."
This Link Takes You to Notes in the Template
STATUS
In this section, please select which action items have been Open (not resolved yet,) Cancelled (No Action Deemed Necessary,) Closed (resolved,) Deferred (put on hold.)
This Link Takes You to Status in the Template