## Project Budget
Weekly Calendar | All
Data
Task | Resources | Baseline Cost | Cost | Actual Cost
GreenBridge-final_schedule_2.0 | Unassigned | 0 | 0 | 0
| Sviluppatore Junior 1 | 14190.4124 | 14190.4094 | 0
| Sviluppatore Junior 2 | 14190.4124 | 14190.4094 | 0
| Data Scientist Junior | 13905.2823 | 13905.2794 | 0
| Specialista QA Junior | 11134.2429 | 11134.2399 | 0
| System Architect Junior | 9962.1147 | 9962.1117 | 0
| Software Engineer Senior | 13931.8713 | 13931.8676 | 0
| Analista Senior | 12654.3999 | 12654.3962 | 0
| Project Manager Senior | 22720.7186 | 22720.7186 | 0
| Heroku Server | 4082.4 | 4082.4 | 0
| Slack | 660 | 660 | 0
GreenBridge-final_schedule_2.0 Totale |  | 117431.8544 | 117431.8324 | 0
Totale complessivo |  | 117431.8544 | 117431.8324 | 0

## Extended Version
Weekly Calendar | All
Data
Task | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Resources | Baseline Cost | Cost | Actual Cost
GreenBridge-final_schedule_2.0 | GreenBridge | Prima Fase | Prima Fase |  |  |  | Slack | 660 | 660 | 0
|  |  | Project Management | Documenti di Iniziazione | Statement Of Work |  | Project Manager Senior | 40 | 40 | 0
[5 empty] | Business Case |  | Project Manager Senior | 200 | 200 | 0
[5 empty] | Project Charter |  | Project Manager Senior | 40 | 40 | 0
|  |  |  | Scope Management | WBS |  | Project Manager Senior | 200 | 200 | 0
[5 empty] | Scope Statement |  | Project Manager Senior | 40 | 40 | 0
|  |  |  | Risk Management | Risk Management Plan |  | Project Manager Senior | 160 | 160 | 0
[5 empty] | Risk Register | Risk Register 1 | Project Manager Senior | 120 | 120 | 0
[6 empty] | Risk Register 2 | Project Manager Senior | 40 | 40 | 0
[6 empty] | Risk Register 3 | Project Manager Senior | 40 | 40 | 0
[6 empty] | Risk Register 4 | Project Manager Senior | 40 | 40 | 0
[6 empty] | Risk Register 5 | Project Manager Senior | 40 | 40 | 0
[6 empty] | Risk Register 6 | Project Manager Senior | 40 | 40 | 0
|  |  |  | Human Resource Plan |  |  | Project Manager Senior | 160 | 160 | 0
|  |  |  | Status Report | Status Report 1 |  | Project Manager Senior | 40 | 40 | 0
[5 empty] | Status Report 2 |  | Project Manager Senior | 40 | 40 | 0
[5 empty] | Status Report 3 |  | Project Manager Senior | 40 | 40 | 0
[5 empty] | Status Report 4 |  | Project Manager Senior | 40 | 40 | 0
[5 empty] | Status Report 5 |  | Project Manager Senior | 40 | 40 | 0
|  |  |  | Cost Monitoring | Cost Monitoring 1 |  | Project Manager Senior | 40 | 40 | 0
[5 empty] | Cost Monitoring 2 |  | Project Manager Senior | 30 | 30 | 0
[5 empty] | Cost Monitoring 3 |  | Project Manager Senior | 30 | 30 | 0
[5 empty] | Cost Monitoring 4 |  | Project Manager Senior | 30 | 30 | 0
[5 empty] | Cost Monitoring 5 |  | Project Manager Senior | 30 | 30 | 0
|  |  |  | Configuration Management | Configuration Management Plan |  | Project Manager Senior | 40 | 40 | 0
[5 empty] | Status Accounting | Status Accounting 1 | Project Manager Senior | 20 | 20 | 0
[6 empty] | Status Accounting 2 | Project Manager Senior | 20 | 20 | 0
[5 empty] | Auditing | Auditing 1 | Specialista QA Junior | 25.6 | 25.6 | 0
[7 empty] | System Architect Junior | 25.6 | 25.6 | 0
[7 empty] | Software Engineer Senior | 32 | 32 | 0
[7 empty] | Analista Senior | 32 | 32 | 0
[7 empty] | Project Manager Senior | 32 | 32 | 0
[6 empty] | Auditing 2 | Sviluppatore Junior 1 | 20 | 20 | 0
[7 empty] | Sviluppatore Junior 2 | 20 | 20 | 0
[7 empty] | Data Scientist Junior | 20 | 20 | 0
[7 empty] | Specialista QA Junior | 20 | 20 | 0
[7 empty] | System Architect Junior | 20 | 20 | 0
[7 empty] | Software Engineer Senior | 25 | 25 | 0
[7 empty] | Analista Senior | 25 | 25 | 0
[7 empty] | Project Manager Senior | 25 | 25 | 0
|  |  | RAD | Analisi del Sistema corrente |  |  | Analista Senior | 160 | 160 | 0
|  |  |  | Definizione dei Requisiti Funzionali e Non Funzionali |  |  | Software Engineer Senior | 40 | 40 | 0
[7 empty] | Analista Senior | 180.05 | 180.05 | 0
|  |  |  | Definizione modello funzionale |  |  | Software Engineer Senior | 40 | 40 | 0
[7 empty] | Analista Senior | 320 | 320 | 0
|  |  |  | Definizione modello oggetti |  |  | Software Engineer Senior | 139.8675 | 139.8675 | 0
[7 empty] | Analista Senior | 80.1325 | 80.1325 | 0
|  |  |  | Definizioni modelli dinamici |  |  | Software Engineer Senior | 165.9259 | 165.9259 | 0
[7 empty] | Analista Senior | 114.0741 | 114.0741 | 0
|  |  |  | Definizione Interfaccia Utente |  |  | Sviluppatore Junior 1 | 40 | 40 | 0
[7 empty] | Sviluppatore Junior 2 | 40 | 40 | 0
[7 empty] | Data Scientist Junior | 16 | 16 | 0
[7 empty] | Software Engineer Senior | 60 | 60 | 0
[7 empty] | Analista Senior | 20 | 20 | 0
|  |  | SDD | Definizione Design Goal e Trade Off |  |  | Data Scientist Junior | 32 | 32 | 0
[7 empty] | System Architect Junior | 80 | 80 | 0
[7 empty] | Software Engineer Senior | 20 | 20 | 0
|  |  |  | Definizione Architettura |  |  | System Architect Junior | 400 | 400 | 0
[7 empty] | Software Engineer Senior | 100 | 100 | 0
|  |  | TP |  |  |  | Specialista QA Junior | 64.0005 | 64.0005 | 0
[7 empty] | Project Manager Senior | 80.0007 | 80.0007 | 0
|  |  | TCS |  |  |  | Specialista QA Junior | 128 | 128 | 0
|  |  | Consegna Intermedia |  |  |  | Unassigned | 0 | 0 | 0
|  |  | ODD | Identificazione Design goals, Trade-offs, COTS e Design Pattern |  |  | Sviluppatore Junior 1 | 32 | 32 | 0
[7 empty] | Sviluppatore Junior 2 | 32 | 32 | 0
[7 empty] | Software Engineer Senior | 80 | 80 | 0
|  |  |  | Specifica delle interfacce |  |  | Sviluppatore Junior 1 | 48 | 48 | 0
[7 empty] | Sviluppatore Junior 2 | 48 | 48 | 0
[7 empty] | Software Engineer Senior | 40 | 40 | 0
|  |  | Prodotto Software | Organizzazione Training e Setup |  |  | Software Engineer Senior | 160 | 160 | 0
[7 empty] | Project Manager Senior | 40 | 40 | 0
|  |  |  | Training |  |  | Sviluppatore Junior 1 | 146.3415 | 146.3415 | 0
[7 empty] | Sviluppatore Junior 2 | 146.3415 | 146.3415 | 0
[7 empty] | Software Engineer Senior | 234.1463 | 234.1463 | 0
[7 empty] | Heroku Server | 100.8 | 100.8 | 0
|  |  |  | GreenBridge 1.0 |  |  | Sviluppatore Junior 1 | 207.84 | 207.84 | 0
[7 empty] | Sviluppatore Junior 2 | 207.84 | 207.84 | 0
[7 empty] | Data Scientist Junior | 208.48 | 208.48 | 0
[7 empty] | Specialista QA Junior | 207.84 | 207.84 | 0
[7 empty] | Software Engineer Senior | 80 | 80 | 0
[7 empty] | Heroku Server | 218.4 | 218.4 | 0
|  |  |  | GreenBridge 2.0 |  |  | Sviluppatore Junior 1 | 264 | 264 | 0
[7 empty] | Sviluppatore Junior 2 | 264 | 264 | 0
[7 empty] | Data Scientist Junior | 264 | 264 | 0
[7 empty] | Specialista QA Junior | 264 | 264 | 0
[7 empty] | Software Engineer Senior | 80 | 80 | 0
[7 empty] | Heroku Server | 235.2 | 235.2 | 0
|  |  | TIR e TSR |  |  |  | Specialista QA Junior | 128 | 128 | 0
|  |  | MU e MI |  |  |  | Sviluppatore Junior 1 | 56 | 56 | 0
[7 empty] | Sviluppatore Junior 2 | 56 | 56 | 0
[7 empty] | Software Engineer Senior | 20 | 20 | 0
|  |  | Matrice di Tracciabilità | Matrice Tracciabilità RAD |  |  | Software Engineer Senior | 7.5 | 7.5 | 0
[7 empty] | Analista Senior | 7.5 | 7.5 | 0
|  |  |  | Matrice Tracciabilità SDD |  |  | System Architect Junior | 4 | 4 | 0
|  |  |  | Matrice Tracciabilità TP |  |  | Specialista QA Junior | 4 | 4 | 0
|  |  |  | Matrice Tracciabilità ODD e Prodotto Software |  |  | Sviluppatore Junior 1 | 11.4286 | 11.4286 | 0
[7 empty] | Sviluppatore Junior 2 | 11.4286 | 11.4286 | 0
[7 empty] | Software Engineer Senior | 11.4286 | 11.4286 | 0
|  |  | Consegna Finale |  |  |  | Unassigned | 0 | 0 | 0
|  |  | Meetings | Scrum "Daily" Meeting | Daily Meeting 1 |  | Sviluppatore Junior 1 | 4 | 4 | 0
[7 empty] | Sviluppatore Junior 2 | 4 | 4 | 0
[7 empty] | Data Scientist Junior | 4 | 4 | 0
[7 empty] | Specialista QA Junior | 4 | 4 | 0
[7 empty] | Software Engineer Senior | 5 | 5 | 0
[5 empty] | Daily Meeting 2 |  | Sviluppatore Junior 1 | 4 | 4 | 0
[7 empty] | Sviluppatore Junior 2 | 4 | 4 | 0
[7 empty] | Data Scientist Junior | 4 | 4 | 0
[7 empty] | Specialista QA Junior | 4 | 4 | 0
[7 empty] | Software Engineer Senior | 5 | 5 | 0
[5 empty] | Daily Meeting 3 |  | Sviluppatore Junior 1 | 4 | 4 | 0
[7 empty] | Sviluppatore Junior 2 | 4 | 4 | 0
[7 empty] | Data Scientist Junior | 4 | 4 | 0
[7 empty] | Specialista QA Junior | 4 | 4 | 0
[7 empty] | Software Engineer Senior | 5 | 5 | 0
[5 empty] | Daily Meeting 4 |  | Sviluppatore Junior 1 | 4 | 4 | 0
[7 empty] | Sviluppatore Junior 2 | 4 | 4 | 0
[7 empty] | Data Scientist Junior | 4 | 4 | 0
[7 empty] | Specialista QA Junior | 4 | 4 | 0
[7 empty] | Software Engineer Senior | 5 | 5 | 0
[5 empty] | Daily Meeting 5 |  | Sviluppatore Junior 1 | 4 | 4 | 0
[7 empty] | Sviluppatore Junior 2 | 4 | 4 | 0
[7 empty] | Data Scientist Junior | 4 | 4 | 0
[7 empty] | Specialista QA Junior | 4 | 4 | 0
[7 empty] | Software Engineer Senior | 5 | 5 | 0
[5 empty] | Daily Meeting 6 |  | Sviluppatore Junior 1 | 4 | 4 | 0
[7 empty] | Sviluppatore Junior 2 | 4 | 4 | 0
[7 empty] | Data Scientist Junior | 4 | 4 | 0
[7 empty] | Specialista QA Junior | 4 | 4 | 0
[7 empty] | Software Engineer Senior | 5 | 5 | 0
[5 empty] | Daily Meeting 7 |  | Sviluppatore Junior 1 | 4 | 4 | 0
[7 empty] | Sviluppatore Junior 2 | 4 | 4 | 0
[7 empty] | Data Scientist Junior | 4 | 4 | 0
[7 empty] | Specialista QA Junior | 4 | 4 | 0
[7 empty] | Software Engineer Senior | 5 | 5 | 0
[5 empty] | Daily Meeting 8 |  | Sviluppatore Junior 1 | 4 | 4 | 0
[7 empty] | Sviluppatore Junior 2 | 4 | 4 | 0
[7 empty] | Data Scientist Junior | 4 | 4 | 0
[7 empty] | Specialista QA Junior | 4 | 4 | 0
[7 empty] | Software Engineer Senior | 5 | 5 | 0
[5 empty] | Daily Meeting 9 |  | Sviluppatore Junior 1 | 4 | 4 | 0
[7 empty] | Sviluppatore Junior 2 | 4 | 4 | 0
[7 empty] | Data Scientist Junior | 4 | 4 | 0
[7 empty] | Specialista QA Junior | 4 | 4 | 0
[7 empty] | Software Engineer Senior | 5 | 5 | 0
[5 empty] | Daily Meeting 10 |  | Sviluppatore Junior 1 | 4 | 4 | 0
[7 empty] | Sviluppatore Junior 2 | 4 | 4 | 0
[7 empty] | Data Scientist Junior | 4 | 4 | 0
[7 empty] | Specialista QA Junior | 4 | 4 | 0
[7 empty] | Software Engineer Senior | 5 | 5 | 0
[5 empty] | Daily Meeting 11 |  | Sviluppatore Junior 1 | 4 | 4 | 0
[7 empty] | Sviluppatore Junior 2 | 4 | 4 | 0
[7 empty] | Data Scientist Junior | 4 | 4 | 0
[7 empty] | Specialista QA Junior | 4 | 4 | 0
[7 empty] | Software Engineer Senior | 5 | 5 | 0
[5 empty] | Daily Meeting 12 |  | Sviluppatore Junior 1 | 4 | 4 | 0
[7 empty] | Sviluppatore Junior 2 | 4 | 4 | 0
[7 empty] | Data Scientist Junior | 4 | 4 | 0
[7 empty] | Specialista QA Junior | 4 | 4 | 0
[7 empty] | Software Engineer Senior | 5 | 5 | 0
[5 empty] | Daily Meeting 13 |  | Sviluppatore Junior 1 | 4 | 4 | 0
[7 empty] | Sviluppatore Junior 2 | 4 | 4 | 0
[7 empty] | Data Scientist Junior | 4 | 4 | 0
[7 empty] | Specialista QA Junior | 4 | 4 | 0
[7 empty] | Software Engineer Senior | 5 | 5 | 0
[5 empty] | Daily Meeting 14 |  | Sviluppatore Junior 1 | 4 | 4 | 0
[7 empty] | Sviluppatore Junior 2 | 4 | 4 | 0
[7 empty] | Data Scientist Junior | 4 | 4 | 0
[7 empty] | Specialista QA Junior | 4 | 4 | 0
[7 empty] | Software Engineer Senior | 5 | 5 | 0
[5 empty] | Daily Meeting 15 |  | Sviluppatore Junior 1 | 4 | 4 | 0
[7 empty] | Sviluppatore Junior 2 | 4 | 4 | 0
[7 empty] | Data Scientist Junior | 4 | 4 | 0
[7 empty] | Specialista QA Junior | 4 | 4 | 0
[7 empty] | Software Engineer Senior | 5 | 5 | 0
|  |  |  | Weekly Meeting | Kick Off Meeting |  | Sviluppatore Junior 1 | 48 | 48 | 0
[7 empty] | Sviluppatore Junior 2 | 48 | 48 | 0
[7 empty] | Data Scientist Junior | 48 | 48 | 0
[7 empty] | Specialista QA Junior | 48 | 48 | 0
[7 empty] | System Architect Junior | 48 | 48 | 0
[7 empty] | Analista Senior | 60 | 60 | 0
[5 empty] | Team Building Meeting |  | Sviluppatore Junior 1 | 36 | 36 | 0
[7 empty] | Sviluppatore Junior 2 | 36 | 36 | 0
[7 empty] | Data Scientist Junior | 36 | 36 | 0
[7 empty] | Specialista QA Junior | 36 | 36 | 0
[7 empty] | System Architect Junior | 36 | 36 | 0
[7 empty] | Analista Senior | 20 | 20 | 0
[5 empty] | Weekly Meeting 3 |  | Sviluppatore Junior 1 | 36 | 36 | 0
[7 empty] | Sviluppatore Junior 2 | 36 | 36 | 0
[7 empty] | Data Scientist Junior | 36 | 36 | 0
[7 empty] | Specialista QA Junior | 36 | 36 | 0
[7 empty] | System Architect Junior | 36 | 36 | 0
[7 empty] | Analista Senior | 45 | 45 | 0
[5 empty] | Weekly Meeting 4 |  | Sviluppatore Junior 1 | 36 | 36 | 0
[7 empty] | Sviluppatore Junior 2 | 36 | 36 | 0
[7 empty] | Data Scientist Junior | 36 | 36 | 0
[7 empty] | Specialista QA Junior | 36 | 36 | 0
[7 empty] | System Architect Junior | 36 | 36 | 0
[7 empty] | Analista Senior | 45 | 45 | 0
[5 empty] | Weekly Meeting 5 |  | Sviluppatore Junior 1 | 12 | 12 | 0
[7 empty] | Sviluppatore Junior 2 | 12 | 12 | 0
[7 empty] | Data Scientist Junior | 12 | 12 | 0
[7 empty] | Specialista QA Junior | 12 | 12 | 0
[7 empty] | System Architect Junior | 12 | 12 | 0
[7 empty] | Analista Senior | 15 | 15 | 0
[5 empty] | Weekly Meeting 6 |  | Sviluppatore Junior 1 | 12 | 12 | 0
[7 empty] | Sviluppatore Junior 2 | 12 | 12 | 0
[7 empty] | Data Scientist Junior | 12 | 12 | 0
[7 empty] | Specialista QA Junior | 12 | 12 | 0
[7 empty] | System Architect Junior | 12 | 12 | 0
[7 empty] | Analista Senior | 15 | 15 | 0
[5 empty] | Weekly Meeting 7 |  | Sviluppatore Junior 1 | 12 | 12 | 0
[7 empty] | Sviluppatore Junior 2 | 12 | 12 | 0
[7 empty] | Data Scientist Junior | 12 | 12 | 0
[7 empty] | Specialista QA Junior | 12 | 12 | 0
[7 empty] | System Architect Junior | 12 | 12 | 0
[7 empty] | Analista Senior | 15 | 15 | 0
[5 empty] | Weekly Meeting 8 |  | Sviluppatore Junior 1 | 12 | 12 | 0
[7 empty] | Sviluppatore Junior 2 | 12 | 12 | 0
[7 empty] | Data Scientist Junior | 12 | 12 | 0
[7 empty] | Specialista QA Junior | 12 | 12 | 0
[7 empty] | System Architect Junior | 12 | 12 | 0
[7 empty] | Analista Senior | 15 | 15 | 0
[5 empty] | Weekly Meeting 9 |  | Sviluppatore Junior 1 | 12 | 12 | 0
[7 empty] | Sviluppatore Junior 2 | 12 | 12 | 0
[7 empty] | Data Scientist Junior | 12 | 12 | 0
[7 empty] | Specialista QA Junior | 12 | 12 | 0
[7 empty] | System Architect Junior | 12 | 12 | 0
[7 empty] | Analista Senior | 15 | 15 | 0
|  |  |  | Sprint Planning Meeting | Sprint Planning Meeting 1 |  | Sviluppatore Junior 1 | 20 | 20 | 0
[7 empty] | Sviluppatore Junior 2 | 20 | 20 | 0
[7 empty] | Data Scientist Junior | 20 | 20 | 0
[7 empty] | Specialista QA Junior | 20 | 20 | 0
[7 empty] | System Architect Junior | 20 | 20 | 0
[7 empty] | Software Engineer Senior | 25 | 25 | 0
[5 empty] | Sprint Planning Meeting 2 |  | Sviluppatore Junior 1 | 20 | 20 | 0
[7 empty] | Sviluppatore Junior 2 | 20 | 20 | 0
[7 empty] | Data Scientist Junior | 20 | 20 | 0
[7 empty] | Specialista QA Junior | 20 | 20 | 0
[7 empty] | System Architect Junior | 20 | 20 | 0
[7 empty] | Software Engineer Senior | 25 | 25 | 0
|  | Seconda Fase | Traning Leaflet |  |  |  | Sviluppatore Junior 1 | 1536 | 1536 | 0
[7 empty] | Sviluppatore Junior 2 | 1536 | 1536 | 0
[7 empty] | Data Scientist Junior | 1536 | 1536 | 0
[7 empty] | Project Manager Senior | 1920 | 1920 | 0
[7 empty] | Heroku Server | 504 | 504 | 0
|  |  | Area Amministrativa e Adesione Mercati |  |  |  | Sviluppatore Junior 1 | 4077.0874 | 4077.0874 | 0
[7 empty] | Sviluppatore Junior 2 | 4077.0874 | 4077.0874 | 0
[7 empty] | Data Scientist Junior | 4077.0874 | 4077.0874 | 0
[7 empty] | Specialista QA Junior | 4077.0874 | 4077.0874 | 0
[7 empty] | System Architect Junior | 3276.7997 | 3276.7997 | 0
[7 empty] | Software Engineer Senior | 5096.3593 | 5096.3593 | 0
[7 empty] | Analista Senior | 4095.9997 | 4095.9997 | 0
[7 empty] | Project Manager Senior | 7286.2236 | 7286.2236 | 0
[7 empty] | Heroku Server | 1008 | 1008 | 0
|  | Terza Fase | Training Flutter |  |  |  | Sviluppatore Junior 1 | 1536 | 1536 | 0
[7 empty] | Sviluppatore Junior 2 | 1536 | 1536 | 0
[7 empty] | Data Scientist Junior | 1536 | 1536 | 0
[7 empty] | Project Manager Senior | 1920 | 1920 | 0
[7 empty] | Heroku Server | 504 | 504 | 0
|  |  | Versione Mobile e Sistema di Push Notifications |  |  |  | Sviluppatore Junior 1 | 5899.7149 | 5899.712 | 0
[7 empty] | Sviluppatore Junior 2 | 5899.7149 | 5899.712 | 0
[7 empty] | Data Scientist Junior | 5899.7149 | 5899.712 | 0
[7 empty] | Specialista QA Junior | 5899.7149 | 5899.712 | 0
[7 empty] | System Architect Junior | 5899.7149 | 5899.712 | 0
[7 empty] | Software Engineer Senior | 7374.6437 | 7374.64 | 0
[7 empty] | Analista Senior | 7374.6437 | 7374.64 | 0
[7 empty] | Project Manager Senior | 9817.4944 | 9817.4944 | 0
[7 empty] | Heroku Server | 1512 | 1512 | 0
| GreenBridge Totale | [6 empty] | 117431.8544 | 117431.8324 | 0
GreenBridge-final_schedule_2.0 Totale | [7 empty] | 117431.8544 | 117431.8324 | 0
Totale complessivo | [7 empty] | 117431.8544 | 117431.8324 | 0